GRITFUEL Growth · Execution · Results

MONTHLY GROWTH PLAYBOOK

CLIENT Helio MAY 2026 · MONTH 3 OF ENGAGEMENT

GROWTH TIER 125 Credits / Month; LEAD STRATEGIST Kim van der Berg; NEXT REVIEW 1 June 2026.

Prepared by GritFuel · gritfuel.works · Confidential

MONTH AT A GLANCE May 2026 · Helio · Growth Tier — 125 credits / month

Month 3 of your GritFuel engagement. Discovery, ICP definition, and positioning are locked. This month we shift into full execution mode across three parallel tracks: messaging refresh, content velocity, and demand generation. All credits are committed.

| THIS MONTH'S FOCUS Execution Brand · Content · Demand | CREDITS ALLOCATED 118 / 125 committed this month | INITIATIVES ACTIVE 3 running in parallel | CREDIT ROLLOVER 7 carry forward to June |
| --- | --- | --- | --- |

CREDIT ALLOCATION — MAY 2026

| Initiative | Deliverables Included | Credits |
| --- | --- | --- |
| 01 · Brand & Messaging Refresh | Positioning doc, messaging house, 3 web page rewrites | 42 |
| 02 · SEO Content Engine | 4 pillar articles, keyword map, internal linking plan | 48 |
| 03 · LinkedIn Demand Generation | Campaign brief, 3 ad sets, copy + creative direction | 28 |
| Rollover to June | Available for ad-hoc requests | 7 |
| TOTAL |  | 125 |

PERFORMANCE SNAPSHOT — APRIL 2026 (Month 2 actuals)

| Metric | Apr Actual | Benchmark | vs. Target | Trend |
| --- | --- | --- | --- | --- |
| Website sessions | 3,240 | 3,000 | +8% | ↑ Growing |
| Organic traffic share | 41% | 35% | +6pp | ↑ Growing |
| LinkedIn page followers | 1,180 | 1,000 | +18% | ↑ Ahead of target |
| Email open rate | 34.2% | 28% | +6.2pp | ↑ Above benchmark |
| Demo requests (inbound) | 7 | 5 | +40% | ↑ Above target |

Note: All metrics are trailing 30-day figures. Demo requests via HubSpot form submissions only.

HOW REVIEWS WORK Your GritFuel engagement model — async-first, one live anchor per month

GritFuel operates on an async-first review model. This keeps delivery moving, protects your timeline, and means you never need to book a call to unblock a piece of work. Every deliverable comes with a structured review brief and a clear feedback window.

| HOW EACH DELIVERABLE IS REVIEWED - Delivered to shared workspace — Google Drive or Notion. You receive a notification with a direct link. - Review brief included — Each deliverable comes with a short note: what to focus on, what decision to make, what feedback format works best. - Feedback via comments — Leave comments directly in the doc. One consolidated feedback round keeps things clean. - 72-hour window — Standard review period. If feedback isn't received, GritFuel will follow up and the revision round carries to the following month. | LIVE SESSIONS - Monthly playbook review (30 min) Included in all tiers. We walk through last month's outcomes, agree this month's priorities, and flag any strategic shifts. - Strategy sessions (as needed) Available as à la carte items when scope requires a live working session — e.g. GTM workshop, positioning sprint. |
| --- | --- |

REVISION ROUNDS

| What's included | How it works |
| --- | --- |
| 1 revision round | Standard for all deliverables. You review, consolidate your feedback into one pass, and GritFuel revises. This is already included in the credit allocation for each initiative. |
| Additional rounds | Each additional revision round uses credits from your monthly allocation or rollover. Rounds are scoped and agreed upfront — you will always know the credit cost before we proceed. |
| Dependencies | Some deliverables are sequential — a later piece cannot begin until an earlier one is approved. These are flagged with a ⚑ symbol in your initiative tables. Timely feedback on flagged items keeps the whole month on track. |

INITIATIVE 01 · Brand & Messaging Refresh 42 credits · Weeks 1–3, May 2026

| Objective | Sharpen Helio's positioning for the enterprise IT buyer segment identified in Month 2 discovery. Rewrite core messaging and update homepage and key product pages to reflect the new ICP and competitive differentiation. |
| --- | --- |
| Approach | Positioning workshop output first, then a messaging hierarchy (category, company, product level). GritFuel rewrites homepage hero, product overview, and pricing page copy. A copy-to-live handoff pack is included. |

Deliverables This Month

| Deliverable | Week | Review window | Status |
| --- | --- | --- | --- |
| Positioning & ICP Narrative Document | Week 1 | 72 hrs | In Progress |
| Messaging House (3-level hierarchy) ⚑ Depends on: Positioning doc approved | Week 2 | 72 hrs | Scheduled |
| Homepage Rewrite (hero + value props) ⚑ Depends on: Messaging house approved | Week 2 | 72 hrs | Scheduled |
| Product Page Rewrite (2 pages) ⚑ Depends on: Messaging house approved | Week 3 | 72 hrs | Scheduled |
| Pricing Page Rewrite ⚑ Depends on: Messaging house approved | Week 3 | 72 hrs | Scheduled |

CLIENT ACTION REQUIRED The positioning document (Week 1) is a hard dependency for all copy work this month. Please review and provide consolidated feedback within 72 hours of delivery to keep the initiative on schedule.

Success Metrics

| KPI | Target | How We Measure |
| --- | --- | --- |
| Messaging clarity (internal review) | 4.5 / 5 | Structured review vs. ICP brief |
| Homepage bounce rate | < 58% | Google Analytics — 30d post-launch |
| Demo conversion (homepage) | > 2.5% | HubSpot form submissions / sessions |

INITIATIVE 02 · SEO Content Engine Launch 48 credits · Weeks 1–4, May 2026

| Objective | Establish Helio's content engine with four high-intent pillar articles targeting decision-stage enterprise buyers. Build the keyword infrastructure and internal linking plan that will compound over 6–12 months. |
| --- | --- |
| Approach | Keyword cluster mapping from current ranking data and competitor gap analysis. Four pillar articles drafted, optimised, and published. Internal linking plan connects pillars to relevant product pages. |

Deliverables This Month

| Deliverable | Week | Review window | Status |
| --- | --- | --- | --- |
| Keyword Cluster Map (8 target clusters) | Week 1 | No review | In Progress |
| Pillar #1 — "IT Monitoring for Scale" | Week 1 | 48 hrs | In Progress |
| Pillar #2 — "Reducing Alert Fatigue" | Week 2 | 48 hrs | Scheduled |
| Pillar #3 — "SRE vs. DevOps Tools" | Week 3 | 48 hrs | Scheduled |
| Pillar #4 — "Enterprise Observability" | Week 4 | 48 hrs | Scheduled |
| Internal Linking Plan | Week 4 | No review | Scheduled |

Success Metrics

| KPI | Target | How We Measure |
| --- | --- | --- |
| Organic impressions (GSC) | +15% MoM by July | Google Search Console |
| Keyword rankings (target terms) | 8 in top 20 by June | Ahrefs rank tracking |
| Blog sessions per article | >250 in first 30 days | Google Analytics |

INITIATIVE 03 · LinkedIn Demand Generation 28 credits · Weeks 2–4 May (live June)

| Objective | Design and brief a 6-week LinkedIn paid campaign targeting VP Engineering and Head of SRE at companies with 200–2,000 employees in DACH and Benelux. Campaign goes live in June following creative production. |
| --- | --- |
| Approach | Campaign architecture, audience strategy, and ad copy produced this month. Creative direction brief prepared for design team. HubSpot attribution configured before launch. Note: paid media ad spend is billed separately. |

Deliverables This Month

| Deliverable | Week | Review window | Status |
| --- | --- | --- | --- |
| Campaign Brief & Architecture | Week 2 | 72 hrs | Scheduled |
| Audience Strategy (3 segments) | Week 2 | 72 hrs | Scheduled |
| Ad Copy — 3 ad sets × 3 variations ⚑ Depends on: Campaign brief approved | Week 3 | 72 hrs | Scheduled |
| Creative Direction Brief ⚑ Depends on: Campaign brief approved | Week 3 | 48 hrs | Scheduled |
| HubSpot Attribution Setup | Week 4 | No review | Scheduled |
| Launch Readiness Report | Week 4 | 48 hrs | Scheduled |

Success Metrics

| KPI | Target | How We Measure |
| --- | --- | --- |
| Cost per lead (CPL) | < 90 credits equiv. | LinkedIn Campaign Manager + HubSpot |
| Click-through rate (CTR) | > 0.6% | LinkedIn Campaign Manager |
| Demo requests from LinkedIn (June) | ≥ 5 in first 2 wks | HubSpot source attribution |

DELIVERY TIMELINE May 2026 — all deliverables, dependencies flagged with ⚑

| Week | Deliverable | Initiative | Review window | Status |
| --- | --- | --- | --- | --- |
| Wk 1 | Positioning & ICP Narrative Document | 01 | 72 hrs | In Progress |
| Wk 1 | Keyword Cluster Map | 02 | No review | In Progress |
| Wk 1 | Pillar #1 — IT Monitoring for Scale | 02 | 48 hrs | In Progress |
| Wk 2 | ⚑ Messaging House (depends on positioning) | 01 | 72 hrs | Scheduled |
| Wk 2 | Homepage Rewrite | 01 | 72 hrs | Scheduled |
| Wk 2 | Pillar #2 — Reducing Alert Fatigue | 02 | 48 hrs | Scheduled |
| Wk 2 | Campaign Brief & Audience Strategy | 03 | 72 hrs | Scheduled |
| Wk 3 | Product Page Rewrite (2 pages) | 01 | 72 hrs | Scheduled |
| Wk 3 | Pricing Page Rewrite | 01 | 72 hrs | Scheduled |
| Wk 3 | Pillar #3 — SRE vs. DevOps Tools | 02 | 48 hrs | Scheduled |
| Wk 3 | ⚑ Ad Copy — 3 ad sets (depends on brief) | 03 | 72 hrs | Scheduled |
| Wk 3 | ⚑ Creative Direction Brief (depends on brief) | 03 | 48 hrs | Scheduled |
| Wk 4 | Pillar #4 — Enterprise Observability | 02 | 48 hrs | Scheduled |
| Wk 4 | Internal Linking Plan | 02 | No review | Scheduled |
| Wk 4 | HubSpot Attribution Setup | 03 | No review | Scheduled |
| Wk 4 | Launch Readiness Report | 03 | 48 hrs | Scheduled |

⚑ Items marked with this symbol have a dependency — they cannot begin until the preceding deliverable is approved.

NEXT MONTH PREVIEW — JUNE 2026

| PLANNED INITIATIVES - LinkedIn campaign goes live — full campaign managed by GritFuel, Wk 1 June - Email nurture sequence — 5-email onboarding drip for trial sign-ups - Mid-funnel case study — first client story from the pilot programme - Monthly review call — 30 min, 1 June 2026. Agenda sent 48 hrs prior. | CREDIT OUTLOOK — JUNE Monthly allocation; 125 cr. + May rollover; + 7 cr. Total available; 132 cr. Est. committed; ~95 cr. |
| --- | --- |

STRATEGIST'S NOTE The positioning document (Week 1) is the dependency that shapes everything else this month. Once that's approved, the rest of the messaging work and the LinkedIn brief all move in parallel. Please prioritise your review and provide consolidated feedback within 72 hours of delivery. I'll send a reminder if the window is close to closing. Kim · Lead Strategist, GritFuel